## Read me
Procure-to-pay requirements workbook
Portfolio case study by Chiamaka Ikpo. Organisation anonymised; process generalised; values illustrative.
Tabs
Summary – requirement and test coverage, calculated with formulas from the other tabs
Stakeholders – stakeholder register with interest, influence and engagement approach
RACI – who is Responsible, Accountable, Consulted and Informed for each activity
Requirements – traceability: pain point → requirement → user story → UAT test cases
UAT Tests – test cases for user acceptance testing; update the Status column during testing
How to use
Blue text = cells you edit (test status, tester, date). Black text = reference content or formulas.
Status values: Not run, Pass, Fail, Blocked. Summary updates automatically.

## Summary
Coverage summary
Priority | Requirements | With ≥1 test | Fully passed | % passed
Must | 12 | 12 | 0 | 0%
Should | 4 | 4 | 0 | 0%
Could | 1 | 1 | 0 | 0%
Total | 17 | 17 | 0 | 0%
UAT status
Not run | 19
Pass | 0
Fail | 0
Blocked | 0
Total test cases | 19
Go-live rule: every Must requirement fully passed (E4 = 100%).
Not ready: Must requirements outstanding

## Stakeholders
ID | Stakeholder | Interest | Influence | Impact on them | Engagement approach | RACI role
SH-01 | Requesting departments | Fast, simple way to buy what they need | Medium | High | Keep informed; involve in UAT | Requester
SH-02 | Procurement team | Fair sourcing, controlled spend, less rework | High | High | Manage closely; co-design | Procurement
SH-03 | Finance / Accounts payable | Invoices match POs and receipts; budget control | High | High | Manage closely; own approval matrix and tolerances | Finance
SH-04 | Compliance & internal audit | Full audit trail, supplier due diligence (KYC) | High | Medium | Manage closely; sign off controls | Compliance
SH-05 | Suppliers | Clear onboarding, on-time payment | Low | Medium | Keep informed | -

## RACI
Activity | Requester | Procurement | Finance | Compliance | One 'A'?
Raise requisition | R/A | I | I | - | OK
Source & select supplier | C | R/A | I | C | OK
Supplier due diligence | - | R | - | A | OK
Approve PO | I | R | A | - | OK
Confirm goods receipt | R/A | I | I | - | OK
Match & pay invoice | - | C | R/A | - | OK
Check: exactly one Accountable per activity

## UAT Tests
Test ID | Story | Acceptance criterion (expected result) | Status | Tester | Date
TC-01 | US-01 | Given a required field is empty, when I try to submit, then the form blocks submission and highlights the field. | Not run
TC-02 | US-01 | Given I have selected a cost centre, then only budget codes valid for that cost centre are shown. | Not run
TC-03 | US-02 | Given a requisition exceeds an approval threshold, when it is approved at one level, then it routes to the next level automatically. | Not run
TC-04 | US-02 | Every approval records the approver, timestamp and decision. | Not run
TC-05 | US-03 | Given a supplier's status is Pending, when a PO is raised for that supplier, then the system blocks it and shows which documents are missing. | Not run
TC-06 | US-04 | Given the invoice, PO and receipt match within tolerance, then the invoice is marked ready for payment. | Not run
TC-07 | US-04 | Given a mismatch, then the invoice goes to the exception queue with the reason. | Not run
TC-08 | US-05 | Given a new supplier, then all checklist documents must be uploaded before status can be set to Verified. | Not run
TC-09 | US-05 | Given a document expires in 30 days, then compliance receives a notification. | Not run
TC-10 | US-06 | Given a requisition assigned to me, when I open it, then I see the cost centre, budget remaining and request value. | Not run
TC-11 | US-06 | Given approving would exceed budget, then I must enter a reason to approve. | Not run
TC-12 | US-07 | Given any requisition, PO or invoice, then I can view every action with user, timestamp and before/after values. | Not run
TC-13 | US-07 | No user, including administrators, can edit or delete audit entries. | Not run
TC-14 | US-08 | Given an approval has not been actioned for 2 working days, then it is sent to the approver's delegate and the requester is notified. | Not run
TC-15 | US-09 | Given goods arrive, when I record the received quantity against the PO, then a goods receipt is created and linked to the PO. | Not run
TC-16 | US-10 | Given I open my requisitions, then each shows its current stage and who it is waiting on. | Not run
TC-17 | US-11 | The report shows requisition-to-PO cycle time, first-time-complete rate, first-time match rate and spend with unverified suppliers (which must be zero). | Not run
TC-18 | US-12 | Given I raised a requisition, then I cannot approve it. | Not run
TC-19 | US-12 | Given I created a supplier, then I cannot approve payments to that supplier. | Not run

## Requirements
ID | Type | Requirement | Priority (MoSCoW) | Pain point | User stories | UAT tests | Tests passed
BR-01 | Business | Every purchase must be traceable from request to payment, including who approved it and when. | Must | P-02, P-03 | US-02, US-07 | 4 | 0
BR-02 | Business | No purchase order may be issued to a supplier whose due diligence is not verified. | Must | P-03 | US-03, US-05 | 3 | 0
BR-03 | Business | Invoices that match the PO and goods receipt within tolerance are paid without manual checking. | Must | P-04 | US-04 | 2 | 0
FR-01 | Functional | The requisition form enforces mandatory fields (item description, quantity, estimated value, cost centre, budget code, need-by date, spend category) and blocks submission until they are complete. | Must | P-01 | US-01 | 2 | 0
FR-02 | Functional | After a cost centre is selected, only budget codes valid for that cost centre are offered. | Must | P-01 | US-01 | 2 | 0
FR-03 | Functional | The system routes each requisition to approvers using the approval matrix (value threshold and spend category). | Must | P-02 | US-02 | 2 | 0
FR-04 | Functional | Approvers see remaining budget for the cost centre alongside the request value. | Should | P-02 | US-06 | 2 | 0
FR-05 | Functional | Approval requests not actioned within 2 working days are escalated to the approver's delegate. | Should | P-02 | US-08 | 1 | 0
FR-06 | Functional | Supplier status (Pending, Verified, Expired, Blocked) is held on the supplier record; a PO cannot be issued unless status is Verified. | Must | P-03 | US-03 | 1 | 0
FR-07 | Functional | Supplier onboarding uses a standard document checklist; compliance is notified 30 days before any document expires. | Should | P-03 | US-05 | 2 | 0
FR-08 | Functional | Requesters confirm goods or service receipt in the system against the PO. | Must | P-04 | US-09 | 1 | 0
FR-09 | Functional | The system matches invoice, PO and goods receipt on quantity and price; matches within tolerance are marked ready for payment, mismatches go to an exception queue with the reason. | Must | P-04 | US-04 | 2 | 0
FR-10 | Functional | Requesters can see the status of their requisition at each stage. | Could | P-01 | US-10 | 1 | 0
FR-11 | Functional | A monthly report shows cycle time, first-time-complete rate, match rate and spend with unverified suppliers. | Should | All | US-11 | 1 | 0
NFR-01 | Non-functional | Every create, approve, reject, change and payment action is logged with user, timestamp and before/after values; the log cannot be edited. | Must | P-02 | US-07 | 2 | 0
NFR-02 | Non-functional | Role-based access; segregation of duties so the same person cannot raise and approve a requisition, or create a supplier and approve a payment to it. | Must | P-02, P-03 | US-12 | 2 | 0
NFR-03 | Non-functional | Audit records are retained for the period required by the bank's record-retention policy. | Must | P-03 | US-07 | 2 | 0